## 1st Sheet
PREPARED |  |  |  | STATUS |  | SECURITY LEVEL
2022-06-17 | Daniel Ardy |  |  | Draft |  | Internal
APPROVED |  |  |  | DOCUMENT KIND |  | PRODUCT ID.
List
TITLE
Names on RACI
OWNING ORGANIZATION |  |  |  | DOCUMENT ID. | PART ID. | REV. | TAG | LANG.
PAPCP |  |  |  | 7PAA004400D0005 |  | A | d3 | en
Revision | Sheet (S) Row (R) |  | Description |  |  | Date Dept./Name
Ad1 |  |  | First draft |  |  | 2022-06-13 PAPCP/RCB Daniel Ardy
Ad2 |  |  | Updated according to 7PAA004400D0005_en_RR |  |  | 2022-06-16 PAPCP/RCB Daniel Ardy
Ad3 |  |  | Updated according to change check comemnts |  |  | 2022-06-17 PAPCP/RCB Daniel Ardy
| © Copyright | 2022 | ABB. All rights reserved.

## Content (hidden)
Overview
All details

## Help
Worksheet: Help
Other useful information
| Role descriptions | Roles see 3BSE014730 Structure and Management of Development Programs and Projects
3BSE088410 Role Descriptions
| Documents | All document types that are listed in RACI are part of our QMS system and can be found under resp. process area.
RACI and "Names on RACI"
This document include information about which document to create during a project. It shows the persons involved and when to create/approve the document. This document is also used as a skeleton for "names on RACI" and then the worksheet Names on RACI is filled in with names on persons who have the different roles.
Worksheet Overview: This worksheet is a another view of the RACI worksheet with only the basic info. As manager you can easily check when different documents shall be ready and who is responsible.
Worksheet RACI: This worksheet has all the information about the documents, where to find the template, when to do them and who is involved. If you have a role in the project it is easy to just use the filter function on row 4 to check which documents you are involved in. You have also the information which roles that are involved e.g. when planning a review and then you get the names from worksheet Names on RACI. The definitions of the letters in the RACI worksheet correspond to the descriptions given in the top left corner of the worksheet and further defined at the bottom of the RACI worksheet. For a limited set of documents, there are two ways of creating the invite for a review. For these documents listed in the worksheet Roles - Viewpoints you can choose the Viewpoints-method or choose the RACI-method see help below.
Worksheet Names on RACI: This worksheet is used when you use this document as a template and here you put names on all RACI roles for your project. Once filled in you find the real names on persons having roles in this project. The comment field can be used for delegation.
Worksheet Invite example - RACI: The worksheet contains an example of the content of an invitation to the review of a document listed in RACI. It is the responsibility of the inviter to ensure all the roles/viewpoints and necessary participants are covered. The participants shall be taken from the Names on RACI worksheet. When using this RACI-method for inviting, it is still preferable to assign viewpoints (requirements, formalities and so on) to the persons who will attend the review as consulted.
Worksheet Invite example - Viewpoints: The worksheet contains an example of the content of an invitation to the review of a document listed in Roles - Viewpoints. It is the responsibility of the inviter to assign each viewpoint to one of the roles marked in the table in worksheet Roles - Viewpoints. All the roles marked shall be invited and given the opportunity to make remarks, but only one shall be assigned to each viewpoint and shall review the document with focus on this area. It is mandatory for each assigned person to participate or send written comments. The Viewpoints-method is an optional way of inviting, intended to help finding persons to cover the different viewpoint areas of the review.
Worksheet Roles-Viewpoints: This worksheet shows the mapping of RACI roles to Review Report viewpoints for a limited set of documents. The use of Viewpoints is an alternativ method for a few documents listed in this worksheet and is intended to help creating an invitation where all relevant roles/viewpoints are covered. One of the roles marked in Viewpoints shall be assigned to each viewpoint but all roles marked in RACI shall be invited and given the opportunity to make remarks.
Worksheet Guidance - Viewpoints: The worksheet contains a guidance on what to keep focus on when reviewing a document from a viewpoint perspective.
Maintenance of this document: When changing roles or documents, be sure that the links to "overview" still works. Lines for process area need to be adjusted if rows added.
--------

## Overview
Worksheet: Overview | [9 empty] | Template: | 3BSE039313
| Gate | [6 empty] | Roles |  | Where to find template | Valid for
| G0 | G1 | G2 | G3 | G4 | G5 | G6 | Responsible | Accountable
[8 empty] | R | A
Requirement Management | [9 empty] | Requirement Management | Title
Development Overview Statement (DOS) | A | [6 empty] | Product Manager | Line Management R&D | Word-Templates | All projects
System Requirements Spec (System RS) | D | A | [5 empty] | Product Manager | Line Management R&D | Word-Templates | System
Market Requirements Spec (MRS) | D | A | [5 empty] | Product Manager | Line Management R&D | Word-Templates | All projects
Safety Requirement Spec (Safety RS) |  | D | A |  |  |  |  | Safety Engineer | Functional Safety Manager (safety) |  | Safety
Product Requirements Spec (PRS) |  | D | A |  |  |  |  | Project Manager | Line Management R&D | Word-Templates | Development
Requirement Traceability matrix |  |  | D |  |  | A |  | Project Manager | Line Management R&D | Excel-Templates | Development
Requirement Change Form/Request (RCR) | [7 empty] | Project Manager | STECO | Word-Templates | All projects
Project management | [9 empty] | Project management | Title
Project Description & Plan |  | D | A |  |  |  |  | Project Manager | Line Management R&D | Word-Templates | All projects
Document Control Plan (DCP) |  |  | D |  |  |  | A | Project Manager | Line Management R&D | Excel-Templates | All projects
User document control plan |  |  | D |  |  | A |  | User Doc. Skribenta Team Lead | Line Management R&D |  | All projects
Document List - Project Baseline |  |  | A |  |  |  |  | Configuration Manager | Line Management R&D |  | All projects
Document List - Architecture Baseline |  |  | D | A |  |  |  | Configuration Manager | Line Management R&D |  | All projects
Document List - Functional Baseline |  |  |  | A |  |  |  | Configuration Manager | Line Management R&D |  | All projects
Document List - Design Baseline |  |  |  | D | A |  |  | Configuration Manager | Line Management R&D |  | All projects
Document List - Test Descriptions Baseline |  |  |  | D | A |  |  | Configuration Manager | Line Management R&D |  | All projects
Document List - Test Records Baseline | [5 empty] | A |  | Configuration Manager | Line Management R&D |  | All projects
Document List - Code Review Records Baseline |  |  |  |  | A |  |  | Configuration Manager | Line Management R&D |  | All projects
Document List - Release Baseline | [5 empty] | D | A | Configuration Manager | Line Management R&D |  | All projects
Troubleshooting Guide | [5 empty] | D | A | Project Manager | Line Management R&D |  | Development
Final Project Report | [6 empty] | A | Project Manager | Line Management R&D | Word-Templates | All projects
Integration | [10 empty] | Title
Product Integration Milestone |  | D | A |  |  |  |  | Project Manager | Line Management R&D | Excel-Templates | All projects
System Integration Plan |  | D | A |  |  |  |  | Project Manager | Line Management R&D | Word-Templates | System
Technical Solution | [9 empty] | Technical Solution | Title
System and Software Criticality Analysis |  |  | D | A |  |  |  | Safety Engineer | Functional Safety Manager (safety) |  | Safety
System FMEA (Failure Mode and Effect Analysis) |  | D | A |  |  |  |  | Safety Engineer | Functional Safety Manager (safety) |  | Safety
Preliminary Hazard Analysis Report |  | D | A |  |  |  |  | Safety Engineer | Functional Safety Manager (safety) |  | Safety
Implementation Proposal (IP) |  |  | A |  |  |  |  | Team/Project Members | Line Management R&D | Word/Excel-Templates | Development
Architecture Specification |  |  | D | A |  |  |  | Product Architect | Line Management R&D |  | Development
Safety System Architecture Specification |  | D | A |  |  |  |  | Safety Engineer | Functional Safety Manager (safety) |  | Safety
Description of Function (DoF) |  |  |  | A |  |  |  | Team/Project Members | Line Management R&D | Word-Templates | Development
Interface Description (IfD) |  |  |  | D | A |  |  | Team/Project Members | Line Management R&D | Word-Templates | Development
Design Description (DD) |  |  |  | D | A |  |  | Team/Project Members | Line Management R&D | Word-Templates | Development
Static Code Analysis Report |  |  |  |  | A |  |  | Project Manager | Line Management R&D |  | SW
Source Code Classification (SCC) |  |  |  | D | A |  |  | Project Manager | Line Management R&D |  | Safety
Parts Lists | [5 empty] | A |  | Project Manager | Line Management R&D |  | HW
Arrangement Drawings | [5 empty] | A |  | Project Manager | Line Management R&D |  | HW
Component Specification |  |  |  |  | A |  |  | Team/Project Members | Line Management R&D |  | HW
Assembly Drawings | [5 empty] | A |  | Project Manager | Line Management R&D |  | HW
Circuit Diagrams |  |  |  | D | A |  |  | Project Manager | Line Management R&D |  | HW
Inspection provision | [5 empty] | A |  | Project Manager | Line Management R&D |  | HW
Hardware FMEDA (Failure Mode Effect and Diagnostic Analysis) | [5 empty] | A |  | Safety Engineer | Line Management R&D |  | Safety
Software HAZOP Report |  |  |  |  | A |  |  | Safety Engineer | Functional Safety Manager (safety) |  | Safety
Safety Manual |  |  |  |  | D | A |  | Safety Engineer | Line Management R&D | Framemaker- | Safety
Reliability data book |  |  |  |  | D | A |  | Safety Engineer | Line Management R&D |  | Safety
User Documentation |  |  |  |  | D | A |  | Technical Product Manager | Product Manager |  | All projects
Cyber Security Assessment |  |  | A |  |  |  |  | Cyber Security Engineer | Head of Cyber Security |  | All projects
Cyber Security Threat Model |  |  | D | A |  |  |  | Product Architect | Head of Cyber Security |  | All projects
Support Strategy |  |  | D |  |  | A |  | Technical Product Manager | Line Management R&D |  | Development
Verification and Validation | [9 empty] | Verification and Validation | Title
Type Test Plan (TTP) |  |  | D | A |  |  |  | Test Responsible | Line Management R&D | Word-Templates | Development
Test Summary and Final Conclusion of Test (Detailed Test Plan) |  |  | D | A |  |  |  | Project Manager | Line Management R&D | Excel-Templates | All projects
Test Summary and Final Conclusion of Test (Final CoT) | [5 empty] | A |  | Project Manager | Line Management R&D | Excel-Templates | Development
Type Test Plan (STT) |  |  | D | A |  |  |  | PJM; STT | Line Management R&D | Word-Templates | STT
Code Review Record |  |  |  |  | A |  |  | Project Manager | Line Management R&D | Word-Templates | SW
Function or Component Type Test Description (FTTD/CTTD) |  |  |  | D | A |  |  | Team/Project Members | Line Management R&D | Word-Templates | Development
Function or Component Type Test Record (FTTR/CTTR) |  |  |  |  | A |  |  | Team/Project Members | Line Management R&D | Word-Templates | Development
Functional Verification Description (FVD) |  |  |  |  | A |  |  | Team/Project Members | Line Management R&D |  | Development
Functional Verification Record (FVR) |  |  |  |  | A |  |  | Team/Project Members | Line Management R&D |  | Development
DesignModule Test Description & Record (DTD) |  |  |  |  | A |  |  | Team/Project Members | Line Management R&D | Word-Templates | Development
DesignModule Test Record (DTR) |  |  |  |  | A |  |  | Team/Project Members | Line Management R&D | Word-Templates | Development
Interface Test Description (LLITD) |  |  |  |  | A |  |  | Team/Project Members | Line Management R&D |  | Development
Interface Test Record (LLITR) |  |  |  |  | A |  |  | Team/Project Members | Line Management R&D |  | Development
Production Test Requirement (PTR) |  |  |  |  | D | A |  | Project Manager | Line Management R&D |  | Development
Environmental Type Test Description (ETTD) |  |  |  | D | A |  |  | Test Responsible | Line Management R&D | Word-Templates | Development
Environmental Type Test Record (ETTR) | [5 empty] | A |  | Project Manager | Line Management R&D | Word-Templates | Development
Product Type Test Description (PTTD) |  |  |  | D | A |  |  | Test Responsible | Line Management R&D | Word-Templates | Development
Product Type Test Record (PTTR) | [5 empty] | A |  | Project Manager | Line Management R&D | Word-Templates | Development
Type Test Description / Environment STT |  |  |  | D | A |  |  | PJM; STT | Line Management R&D |  | STT
Type Test Record / Environment STT | [5 empty] | A |  | PJM; STT | Line Management R&D |  | STT
Safety Validation Test Description (SVTD) |  |  |  |  | A |  |  | Test Responsible | Line Management R&D |  | Safety
Safety Validation Test Record (SVTR) | [5 empty] | A |  | Project Manager | Line Management R&D |  | Safety
Standard Regression Test Description |  |  |  |  | A |  |  | Test Responsible | Line Management R&D |  | Development
Type Test List (FTT/CTT) | [6 empty] | A | Project Manager | Line Management R&D | Word-Templates | Development
Traceability report (FTT and PTT) |  |  |  |  | A |  |  | Project Manager | Line Management R&D |  | Safety
Safety Manual Justification |  |  |  |  | A |  |  | Project Manager | Line Management R&D | Framemaker- | Safety
Justification report (Requirements-Functions) |  |  |  |  | A |  |  | Project Manager | Line Management R&D |  | Safety
Type Test List (PTT) | [6 empty] | A | Project Manager | Line Management R&D | Word-Templates | Development
Type Test List for System Type Test |  |  |  |  | D |  | A | PJM; STT | Line Management R&D | Word-Templates | System
Checklist for Beta & start of PTT (use Checklist for Beta IVA and Start of Type Tests) |  |  |  |  | A |  |  | Project Manager | Line Management R&D | Excel-Templates | Development
Checklist for start of STT (use Checklist for Beta IVA and Start of Type Tests) |  |  |  |  | A |  |  | PJM; STT | LM; STT | Excel-Templates | STT
Checklist for start of RAT (use Checklist for Beta IVA and Start of Type Tests) | [5 empty] | A |  | PJM; STT | LM; STT | Excel-Templates | STT
Checklist for IVA (use Checklist for Beta IVA and Start of Type Tests) | [5 empty] | A |  | PJM; STT | LM; STT | Excel-Templates | Development
Checklist for start of SVT (use Checklist for Beta IVA and Start of Type Tests) | [5 empty] | A |  | Project Manager | Line Management R&D | Excel-Templates | Safety
Names on RACI |  |  | A |  |  |  |  | Project Manager | Line Management R&D | Excel-Templates | All projects
Quality Assurance | [9 empty] | Quality Assurance | Title
Quality Plan / Q&Safety Plan |  |  | A |  |  |  |  | Project Manager | Line Management R&D | Word-Templates | All projects
Quality System Overview |  | D | A |  |  |  |  | Quality Engineer | Line Management R&D | Excel-Templates | Development
Configuration Management | [9 empty] | Configuration Management | Title
Configuration Management Plan (for project) |  |  | A |  |  |  |  | Configuration Manager | Line Management R&D | Word-Templates | All projects
FCA Checklist and Report (Functional Configuration Audit) |  |  |  |  | D | A |  | Configuration Manager | Product Manager | Word-Templates | All projects
PCA Checklist and Report (Physical Configuration Audit) | [5 empty] | A |  | Configuration Manager | Product Manager | Word-Templates | All projects
Safety tool selection report | [7 empty] | Team/Project Members | Line Management R&D | Word-Templates | Safety
T3 Tool Defect Analysis | [7 empty] | Team/Project Members | Line Management R&D |  | Safety
Impact Analysis Report |  |  | D |  |  | A |  | Project Manager | Functional Safety Manager (safety) | Word-Templates | Safety
Baseline Plan |  |  | A |  |  |  |  | Configuration Manager | Line Management R&D | Word-Templates | All projects
Version List | [5 empty] | A |  | Configuration Manager | Line Management R&D | Word-Templates | All projects
Version Specification | [5 empty] | A |  | Configuration Manager | Line Management R&D | Word-Templates | All projects
Productization | [9 empty] | Productization | Title
Product guide |  |  | D |  | A |  |  | Project Manager | Product Manager |  | All projects
Ex Application Report (Technical Report) |  |  |  |  | D | A |  | EX Component Responsible | Line Management R&D |  | All projects
Release Notes | [5 empty] | A |  | Project Manager | Product Manager |  | All projects
Released User Documentation | [5 empty] | A |  | User Doc. Skribenta Team Lead | Product Manager |  | All projects
General Export Control Input Data Report (input to PCE) |  |  | D |  | A |  |  | Project Manager | Line Management R&D |  | All projects
System Software Version | [5 empty] | A |  | Configuration Manager | Line Management R&D |  | System
Product Maintenance | [9 empty] | Product Maintenance
Checklist for rollup |  |  | A |  |  |  |  | Project Manager | Line Management R&D | Excel-Templates | Rollups
Checklist for temporary correction | [5 empty] | A |  | Technical Product Manager | Line Management R&D | Excel-Templates | Temp. Correction
D= Draft A= Approved
Note on C2: Remember that if data is changed most of the documents need to be re-approved again.
Note on M2: Use multiple choice to select what documents you need. * select "All projects" * select type of project like "system","STT","Development",.. * select included parts like "HW","SW","safety"…. If you want to see the headlines aswell also choose "title"
Note on E53: Approval at G2 and G5.

## RACI
3BSE039313 RACI Chart, worksheet RACI | Product/System Project | [19 empty] | External |  |  |  | Line | [9 empty] | R | Ready at Gate |  | Safety |  |  | Templates
R = Responsible (author) A = Accountable (approving person) C = Consulted (review) I = Informed (carbon copy) CS=consulted when System Project Explanations: see below | STECO | Project Manager | Technical Coordinator (Product Owner) | Configuration Manager | Test Responsible | PJM; STT | PJM; S100CI871 | PJM; Endurance PM | PJM; Endurance CI | Productization | Product Architect | Team/Subproject Leaders | Team/Project Members | Software analyst | Hardware analyst | Cyber Security Engineer | Quality Engineer | Safety Engineer | EX Representative | EX Component Responsible | QA Person; CFA Project | SA Person; CFA Project | System Architect | User Doc. Skribenta Team Lead | Product Manager | Technical Product Manager | Line Management R&D | Line Management TPM | Line Management Quality | LM; STT | LM; SupportLine | LM; Sales and Market Communication | Head of Cyber Security | Functional Safety Manager (safety) | Formal review record (N/Y/P) | Draft | Approved | Safety team to communicate with certifying body (E) | Document only applicable for safety products | Mandatory for Safety Projects | Where to find | Valid for | Comments
FILTER
Requirement Management | [41 empty] | Title
Development Overview Statement (DOS) | C | C | [22 empty] | R | I | A | [7 empty] | P |  | G0 |  |  |  | Word-Templates | All projects
System Requirements Spec (System RS) | C | C | I | I | C | I | I | I | I |  |  | I |  |  |  | C |  | I |  |  |  |  | I |  | R | I | A |  |  |  |  | I | I |  | Y | G0 | G1 |  |  | Y | Word-Templates | System
Market Requirements Spec (MRS) | I | C | I | I | C | I | I | I | I |  |  | I |  |  |  | I |  | I | C |  | I |  |  |  | R | I | A |  |  |  |  | I | I |  | Y | G0 | G1 |  |  | Y | Word-Templates | All projects
Safety Requirement Spec (Safety RS) | I | C | I | I | C |  |  |  |  | I |  | I | I |  |  | I |  | R |  |  | I | I |  |  | C | C |  |  |  |  | I |  |  | A | Y | G1 | G2 | C | Y | Y |  | Safety
Product Requirements Spec (PRS) | I | R | I | I | C |  |  |  |  | I |  | I | I |  |  | C |  | C | C | I | I | I |  |  | C | C | A |  |  |  | I |  | I |  | Y | G1 | G2 | E |  |  | Word-Templates | Development
Requirement Traceability matrix | I | R | I | I | I |  |  |  |  | I |  | I | I |  |  |  |  | C | C | [5 empty] | C |  | A |  |  |  | I |  |  |  | Y | G2 | G5 | E |  |  | Excel-Templates | Development
Requirement Change Form/Request (RCR) | A | R | I | I |  | I | I | I | I |  |  | I |  |  |  | I |  | C | C | I |  |  | CS |  | C | C | I | [7 empty] | P |  |  |  |  | Y | Word-Templates | All projects
Project management | [41 empty] | Title
Project Description & Plan | C | R | I | C | I | I | I | I | I | I |  | I |  |  |  | I | C | C | C |  | I | I |  |  | C | I | A | [5 empty] | I | I | Y | G1 | G2 | E |  | Y | Word-Templates | All projects
Document Control Plan (DCP) |  | R |  | C | [12 empty] | C | I | C | [7 empty] | A | [7 empty] | N | G2 | G6 | E |  | Y | Excel-Templates | All projects
User document control plan | I | C |  | C | I |  |  |  |  | I | [6 empty] | C | C | C |  |  |  |  | R | C | C | A |  |  | C |  |  |  |  | N | G2 | G5 |  |  |  |  | All projects
Document List - Project Baseline |  | C |  | R | [12 empty] | I | C |  |  | I | [5 empty] | A | [7 empty] | Y |  | G2 |  |  | Y |  | All projects
Document List - Architecture Baseline |  | C |  | R | [6 empty] | I | [5 empty] | I | C |  |  | I |  |  |  | I | C | A | [7 empty] | Y | G2 | G3 |  |  | Y |  | All projects
Document List - Functional Baseline |  | C |  | R | [7 empty] | C |  |  |  |  | I | C |  |  | I |  |  |  | I | C | A | [7 empty] | Y |  | G3 |  |  | Y |  | All projects
Document List - Design Baseline |  | C |  | R | [7 empty] | C |  |  |  |  | I | C |  |  | I |  |  |  | I | C | A | [7 empty] | Y | G3 | G4 |  |  | Y |  | All projects
Document List - Test Descriptions Baseline |  | C |  | R | I | [6 empty] | C |  |  |  |  | I | C |  |  | I |  |  |  | I | C | A | [7 empty] | Y | G3 | G4 |  |  | Y |  | All projects | Shall be approved before start of formal test which for some test levels are before G4.
Document List - Test Records Baseline |  | C |  | R | I | [6 empty] | C |  |  |  |  | I | C |  |  | I |  |  |  | I | C | A | [7 empty] | Y |  | G5 |  |  | Y |  | All projects
Document List - Code Review Records Baseline |  | C |  | R | [7 empty] | C |  |  |  |  | I | C |  |  | I |  |  |  | I | C | A | [7 empty] | Y |  | G4 |  |  | Y |  | All projects
Document List - Release Baseline |  | C |  | R | [5 empty] | I | [6 empty] | I | C | C |  | I |  |  | I | I | C | A | [7 empty] | Y | G5 | G6 |  |  | Y |  | All projects
Troubleshooting Guide |  | R |  |  | I | I | I | I | I |  | I | I | I | [12 empty] | I | A |  |  |  | C |  |  |  | N | G5 | G6 |  |  |  |  | Development
Final Project Report |  | R | I | I | I | I | I | I | I | I | I | C | I |  |  | I |  |  |  |  | I | I |  |  | I |  | A | [7 empty] | N |  | G6 |  |  |  | Word-Templates | All projects
Integration | [41 empty] | Title
Product Integration Milestone | I | R |  | I | I | [6 empty] | C |  |  |  | I | C | I |  |  | I |  |  |  | I | I | A | [7 empty] | N | G1 | G2 |  |  |  | Excel-Templates | All projects
System Integration Plan | I | R |  | I |  | C | C | C | C |  |  | C |  |  |  | I | C | [7 empty] | I | I | A |  |  | I |  |  | I |  | Y | G1 | G2 |  |  |  | Word-Templates | System
Technical Solution | [41 empty] | Title
System and Software Criticality Analysis |  | I | I | [8 empty] | I | C |  |  | I |  | R |  |  |  | I | [11 empty] | A | Y | G2 | G3 | E | Y | Y |  | Safety
System FMEA (Failure Mode and Effect Analysis) |  | I | I | [8 empty] | I | C |  |  |  |  | R |  |  |  | I |  |  |  | I | [7 empty] | A | Y | G1 | G2 | C | Y | Y |  | Safety
Preliminary Hazard Analysis Report |  | I | I | [9 empty] | C |  |  |  |  | R |  |  |  | I |  |  |  | I | [7 empty] | A | Y | G1 | G2 | E | Y | Y |  | Safety
Implementation Proposal (IP) |  | I | I | I |  | I | I | I | I |  | C | C | R |  |  | C |  | C | C | C |  |  | CS |  | C | C | A | [7 empty] | Y |  | G2 |  |  |  | Word/Excel-Templates | Development
Architecture Specification |  | I | I | I | [6 empty] | R | I | I |  |  | C |  | C | C |  |  |  | C |  |  |  | A | [7 empty] | Y | G2 | G3 | E |  | Y |  | Development
Safety System Architecture Specification |  | I | I | I | I | [5 empty] | C | I | I |  |  | I |  | R |  |  |  |  | I |  | I | I | [7 empty] | A | Y | G1 | G2 | E | Y | Y |  | Safety
Description of Function (DoF) |  | C | C |  | C |  |  |  |  | I | C | C | R | I | I | C | C | C | C | C |  |  |  |  | C | C | A | [7 empty] | Y |  | G3 | E |  | Y | Word-Templates | Development
Interface Description (IfD) |  | C | C | [7 empty] | C | C | R |  |  | C | C | C | [8 empty] | A | [7 empty] | Y | G3 | G4 | E |  | Y | Word-Templates | Development
Design Description (DD) |  | C | C | [7 empty] | C | C | R |  |  | C | C | C |  | C | [6 empty] | A | [7 empty] | Y | G3 | G4 | E |  | Y | Word-Templates | Development
Static Code Analysis Report |  | R |  | I | [7 empty] | I |  | C |  | C | C | C | [8 empty] | A | [7 empty] | Y |  | G4 | E | Y | Y |  | SW
Source Code Classification (SCC) |  | R | [9 empty] | C | C |  |  |  |  | C | [8 empty] | A | [7 empty] | Y | G3 | G4 |  | Y | Y |  | Safety
Parts Lists |  | R |  | I | [8 empty] | C |  | I |  | C | C |  | C | [6 empty] | A | [7 empty] | Y |  | G5 |  |  |  |  | HW
Arrangement Drawings |  | R | [10 empty] | C |  | I |  | C |  |  | C | [6 empty] | A | [7 empty] | Y |  | G5 |  |  |  |  | HW
Component Specification |  | I | [9 empty] | C | R |  |  |  | C | C |  | C | [5 empty] | I | A | [7 empty] | Y |  | G4 |  |  |  |  | HW | Drawings for mechanical parts and electrical components including Label drawings
Assembly Drawings |  | R | [10 empty] | C |  | I |  | C |  |  | C | [6 empty] | A | [7 empty] | Y |  | G5 |  |  |  |  | HW
Circuit Diagrams |  | R | [10 empty] | C | I | I |  | C | C |  | C | [6 empty] | A | [7 empty] | Y | G3 | G4 |  |  |  |  | HW
Inspection provision |  | R | [10 empty] | C |  |  |  | C |  |  | C | [6 empty] | A | [7 empty] | N |  | G5 |  |  |  |  | HW | When reviewed add a check-in comment in DMS.
Hardware FMEDA (Failure Mode Effect and Diagnostic Analysis) |  | C | [10 empty] | C | I | I |  | C | R | [8 empty] | A | [7 empty] | Y |  | G5 | E | Y | Y |  | Safety
Software HAZOP Report |  | I | I | [8 empty] | I | C | I |  |  |  | R | [15 empty] | A | P |  | G4 | E | Y | Y |  | Safety
Safety Manual |  | I | [7 empty] | I |  | I | I |  |  |  | C | R | [5 empty] | C | I | I | A | [7 empty] | Y | G4 | G5 | C | Y | Y | Framemaker- | Safety
Reliability data book |  | I | [7 empty] | C |  | I | I |  |  |  | C | R | [5 empty] | C | I | C | A | [7 empty] | Y | G4 | G5 | C | Y | Y |  | Safety
User Documentation |  |  |  |  | I |  |  |  |  | I |  | C | C |  |  | C | C | C | C | I |  |  |  | C | A | R | [8 empty] | Y | G4 | G5 | E |  |  |  | All projects
Cyber Security Assessment |  | I | [8 empty] | C | I |  |  |  | R |  | I |  |  | I |  |  |  | I | C | [6 empty] | A |  | N |  | G2 |  |  |  |  | All projects | Approval at G2 and G5.
Cyber Security Threat Model |  | I |  |  | C | [5 empty] | R | C |  |  |  | C |  | I |  |  | I |  |  |  | I | I | [6 empty] | A |  | Y | G2 | G3 |  |  |  |  | All projects
Support Strategy |  | I | [16 empty] | C | [5 empty] | C | R | A |  |  |  | C |  |  |  | Y | G2 | G5 |  |  |  |  | Development
Verification and Validation | [41 empty] | Title
Type Test Plan (TTP) |  | C | I | C | R | [6 empty] | I | I |  |  | C | C | C | C | C |  |  |  |  | I | I | A | [5 empty] | I | I | Y | G2 | G3 | E |  | Y | Word-Templates | Development
Test Summary and Final Conclusion of Test (Detailed Test Plan) |  | R | I | I | C | [6 empty] | I |  |  |  | C | C | C | C | [5 empty] | I | I | A | [7 empty] | Y | G2 | G3 |  |  | Y | Excel-Templates | All projects
Test Summary and Final Conclusion of Test (Final CoT) |  | R | I | C | C | [6 empty] | I |  |  |  | I | C | C |  | I | I | I |  |  | I | C | A | [7 empty] | P |  | G5 |  | Y | Y | Excel-Templates | Development
Type Test Plan (STT) |  | C | I | I | I | R | R | R | R |  |  | I |  |  |  | C | C | [7 empty] | I | I | A | [7 empty] | Y | G2 | G3 |  |  |  | Word-Templates | STT
Code Review Record |  | R | [9 empty] | I | C | I |  | I | [10 empty] | A | [7 empty] | N |  | G4 |  |  | Y | Word-Templates | SW
Function or Component Type Test Description (FTTD/CTTD) |  | C |  |  | C | [6 empty] | C | R |  |  | I | C | C |  | C | [6 empty] | A | [7 empty] | Y | G3 | G4 |  |  | Y | Word-Templates | Development
Function or Component Type Test Record (FTTR/CTTR) |  | I |  |  | I | [6 empty] | C | R |  |  | I | C | C |  | C | [6 empty] | A | [7 empty] | P |  | G4 |  |  | Y | Word-Templates | Development | Reviewed by maximum one person technical with domain competence
Functional Verification Description (FVD) |  | I |  |  | C | [6 empty] | I | R |  | I |  | C | C | [8 empty] | A | [7 empty] | Y |  | G4 |  |  | Y |  | Development
Functional Verification Record (FVR) |  | I | [10 empty] | R |  | I |  | C | C | [8 empty] | A | [7 empty] | P |  | G4 |  |  | Y |  | Development
DesignModule Test Description & Record (DTD) |  | C |  |  | I | [6 empty] | C | R |  |  | I | C | C | [8 empty] | A | [7 empty] | Y |  | G4 |  |  | Y | Word-Templates | Development | When created as a test description
DesignModule Test Record (DTR) |  | I |  |  | I | [6 empty] | C | R |  |  | I | C | C | [8 empty] | A | [7 empty] | P |  | G4 |  |  | Y | Word-Templates | Development | When used as a test record. Reviewed by maximum one person technical with domain competence
Interface Test Description (LLITD) |  | I |  |  | I | [6 empty] | C | R |  |  | I | C | C | [8 empty] | A | [7 empty] | Y |  | G4 |  |  | Y |  | Development
Interface Test Record (LLITR) |  | I |  |  | I | [6 empty] | C | R |  |  | I | C | C | [8 empty] | A | [7 empty] | P |  | G4 |  |  | Y |  | Development
Production Test Requirement (PTR) |  | R | [7 empty] | C |  |  | I |  | I |  |  |  |  | C | [6 empty] | A | [7 empty] | Y | G4 | G5 |  |  |  |  | Development
Environmental Type Test Description (ETTD) |  |  |  |  | R | [6 empty] | C | I |  | I |  | C | C | I | C | [5 empty] | I | A | [7 empty] | Y | G3 | G4 |  |  | Y | Word-Templates | Development
Environmental Type Test Record (ETTR) |  | R |  |  | I | [6 empty] | I | I |  | I |  | C | C |  | C | [5 empty] | C | A | [7 empty] | P |  | G5 |  |  | Y | Word-Templates | Development
Product Type Test Description (PTTD) |  | C |  |  | R | [6 empty] | C | C |  |  | I | C | C | I | C | [5 empty] | C | A | [7 empty] | Y | G3 | G4 |  |  | Y | Word-Templates | Development
Product Type Test Record (PTTR) |  | R |  |  | I | [6 empty] | I |  |  |  | I | C | C |  | C | [5 empty] | C | A | [7 empty] | P |  | G5 |  |  | Y | Word-Templates | Development
Type Test Description / Environment STT |  | I |  |  |  | R | R | R | R |  |  | C | I |  | I |  | C | I |  |  | C |  |  |  | I | C | A | [7 empty] | Y | G3 | G4 |  |  |  |  | STT
Type Test Record / Environment STT |  | I |  |  | I | R | R | R | R |  |  | I | I |  | I |  | C | I | [7 empty] | C | A | [7 empty] | P |  | G5 |  |  |  |  | STT
Safety Validation Test Description (SVTD) |  | C |  |  | R | [6 empty] | C | C |  |  |  | C | C | [6 empty] | I | C | A | [7 empty] | Y |  | G4 | E | Y | Y |  | Safety
Safety Validation Test Record (SVTR) |  | R |  |  | I | [6 empty] | I |  |  |  |  | C | C | [7 empty] | C | A | [7 empty] | P |  | G5 | E | Y | Y |  | Safety
Standard Regression Test Description |  |  | I |  | R | I | I | I | I | [8 empty] | C |  |  |  | I |  |  |  | I | A | [7 empty] | Y |  | G4 | E |  | Y |  | Development
Type Test List (FTT/CTT) |  | R |  | I | [11 empty] | I | C | I |  |  | C |  |  |  |  | C | A | [7 empty] | Y |  | G6 |  |  |  | Word-Templates | Development
Traceability report (FTT and PTT) |  | R | C | I | C | [6 empty] | I | [5 empty] | C | [7 empty] | C | A | [7 empty] | Y |  | G4 | E | Y | Y |  | Safety
Safety Manual Justification |  | R |  | I | C | [6 empty] | I |  |  |  |  | C | C | [8 empty] | A | [7 empty] | Y |  | G4 | E | Y | Y | Framemaker- | Safety
Justification report (Requirements-Functions) |  | R | C | I | [7 empty] | I | [5 empty] | C | [7 empty] | I | A | [7 empty] | Y |  | G4 | E | Y | Y |  | Safety
Type Test List (PTT) |  | R |  | I | [7 empty] | I |  |  |  | I |  | I |  |  | C |  |  |  | I | C | A | [7 empty] | Y |  | G6 |  |  |  | Word-Templates | Development
Type Test List for System Type Test |  |  |  | I |  | R | R | R | R |  |  | I |  |  |  | I |  | I |  |  | C |  |  |  |  | C | A | [7 empty] | Y | G4 | G6 |  |  |  | Word-Templates | System
Checklist for Beta & start of PTT (use Checklist for Beta IVA and Start of Type Tests) |  | R |  | C | C | [10 empty] | C |  | C |  |  | C | C |  |  |  | C | A | [7 empty] | P |  | G4 |  |  | Y | Excel-Templates | Development
Checklist for start of STT (use Checklist for Beta IVA and Start of Type Tests) |  | C |  | C | C | R | R | R | R | [11 empty] | C |  |  |  |  | C |  |  |  | A |  |  |  |  | P |  | G4 |  |  |  | Excel-Templates | STT
Checklist for start of RAT (use Checklist for Beta IVA and Start of Type Tests) |  | C |  | C | C | R | R | R | R | [11 empty] | C |  |  |  |  | C |  |  |  | A |  |  |  |  | P |  | G5 |  |  |  | Excel-Templates | STT
Checklist for IVA (use Checklist for Beta IVA and Start of Type Tests) |  | C |  | C |  | R | R | R | R | [7 empty] | C | C |  |  | C | C |  |  |  | C |  |  |  | A |  |  |  |  | P |  | G5 |  |  | Y | Excel-Templates | Development
Checklist for start of SVT (use Checklist for Beta IVA and Start of Type Tests) |  | R |  | C | C | [12 empty] | C |  |  | C |  |  |  |  | C | A | [7 empty] | P |  | G5 |  | Y | Y | Excel-Templates | Safety | Shall be approved before formal SVT starts.
Names on RACI | I | R |  | I | [5 empty] | I | [5 empty] | I | C | C | C |  | C | C |  | I |  |  | A | [7 empty] | Y |  | G2 |  |  | Y | Excel-Templates | All projects
Quality Assurance | [41 empty] | Title
Quality Plan / Q&Safety Plan | I | R | I | C | I | I | I | I | I | I |  | I |  |  |  | I | C | C | C |  | C | C |  |  |  |  | A | [5 empty] | I | A | Y |  | G2 | E | Y | Y | Word-Templates | All projects
Quality System Overview |  | I | I | C | [7 empty] | I |  |  |  | I | R | C | C |  | C | [5 empty] | A | [5 empty] | I |  | Y | G1 | G2 |  |  | Y | Excel-Templates | Development
Configuration Management | [41 empty] | Title
Configuration Management Plan (for project) | I | C | I | R | I | I | I | I | I | I | I | I | I |  |  | I | C | C | [6 empty] | I | C | A | [5 empty] | I |  | Y |  | G2 | E |  | Y | Word-Templates | All projects
FCA Checklist and Report (Functional Configuration Audit) | I | C |  | R | C | [10 empty] | I | C | I |  |  | I |  |  |  | A | [10 empty] | G4 | G5 |  |  |  | Word-Templates | All projects
PCA Checklist and Report (Physical Configuration Audit) | I | C |  | R | C | [10 empty] | I | C | I |  |  | I |  |  |  | A | [11 empty] | G5 |  |  |  | Word-Templates | All projects
Safety tool selection report |  | C | C | C | [8 empty] | R | C | C |  |  | C | [8 empty] | A | [7 empty] | Y |  |  | C | Y | Y | Word-Templates | Safety | A safety tool selection report shall be approved before using a new or updated tool.
T3 Tool Defect Analysis |  |  |  | I | [6 empty] | I |  | R | I |  |  |  | C |  |  |  |  | I |  |  |  | A | [7 empty] | Y |  |  |  | Y | Y |  | Safety
Impact Analysis Report |  | R | C | I | C | [6 empty] | C | [5 empty] | C | I | C |  | I | [11 empty] | A | Y | G2 | G5 | E | Y | Y | Word-Templates | Safety
Baseline Plan |  | I | I | R | [5 empty] | I |  | I | [13 empty] | C | A | [7 empty] | Y |  | G2 |  |  |  | Word-Templates | All projects
Version List |  | I |  | R | [11 empty] | I |  | I | [7 empty] | C | A | [7 empty] | Y |  | G5 |  |  | Y | Word-Templates | All projects
Version Specification |  | I |  | R | [11 empty] | I |  | I | [7 empty] | C | A | [7 empty] | Y |  | G5 |  |  | Y | Word-Templates | All projects
Productization | [41 empty] | Title
Product guide |  | R | [9 empty] | I | C |  |  | I |  | C | C | I |  |  |  | C | A | C | [5 empty] | I | I |  | Y | G2 | G4 |  |  |  |  | All projects
Ex Application Report (Technical Report) |  | I | [9 empty] | I | C |  |  |  |  | I | C | R |  |  |  |  | I | C | A | [7 empty] | Y | G4 | G5 |  |  |  |  | All projects
Release Notes |  | R | I | I |  | I | I | I | I |  |  | I | C |  |  | I |  | C | C | I | I |  |  | C | A | C |  |  |  |  | I | C |  |  | Y |  | G5 | E |  |  |  | All projects
Released User Documentation |  | I |  | I | [7 empty] | C | [5 empty] | C | [5 empty] | R | A | C | [8 empty] | Y |  | G5 |  |  |  |  | All projects
General Export Control Input Data Report (input to PCE) |  | R |  | I | [5 empty] | C |  |  | C | C | C | [9 empty] | C | C | A | [7 empty] | N | G2 | G4 |  |  |  |  | All projects | PCE - Product Classification Engineer
System Software Version |  | I | I | R | [7 empty] | I |  |  |  | I |  | C |  |  | I |  |  |  | I | C | A | [7 empty] | Y |  | G5 |  |  |  |  | System
Product Maintenance
Checklist for rollup | C | R |  | C | [9 empty] | C |  | I | C | C | C |  | C | I |  |  | I | C | A |  |  |  | I | [5 empty] | G2 | E |  |  | Excel-Templates | Rollups
Checklist for temporary correction |  |  |  | C | [11 empty] | I |  |  | C |  | C |  |  |  | I | R | A |  |  |  | I | [5 empty] | G5 |  |  |  | Excel-Templates | Temp. Correction
Notes:
In cases when steering committee is accountable, chairman signs approval.
R | Responsible: the person responsible for producing the document under review also responsible for calling to the review. The production and calling to review can be delegated.
A | Accountable: this person has the power to make the final decision. Invited to review meeting as optional. All document with an "A" shall be formally approved. (Note: There are document types that requires more than one approvers).
C | Consulted: The role shall be informed when a review is made and are required to either participate, leave written comments, or delegate. The role could, when relevant, be consulted before the document is completed, the role should during this consulting time provide information for making the document correct and suggestions on what to remove from the document. In some cases, where more that one person is assigned, only relevant persons with the role need to be invited (Example Project Members - maybe not all the project members need to be invited depending on technical area or product).
I | Informed: The role shall be informed of any review of the document and have the possibility to give written feedback. The role could, when relevant, be consulted before the document is completed, the role should during this consulting time provide information for making the document correct and suggestions on what to remove from the document.
E | Adequate information shall be communicated to the external certification body .
N | Informal review recommended
Y | A "Y" means Yes and for column "formal review record" it means a formal Review meeting need to be held and separate formal Review Record need to be written.
P | A formal Review meeting need to be held and documented e.g.. in MoM or in the document itself ( no formal RR needed).
Note on B2: If there are several stecos they have to decide which document that has to be reviewed by which steco.
Note on S2: Mandatory for safety development only
Note on AJ2: See description beneath RACI for explanation of N/Y/P
Note on AQ2: Use multiple choice to select what documents you need. * select "All projects" * select type of project like "system","STT","Development",.. * select included parts like "HW","SW","safety"…. If you want to see the headlines aswell also choose "title"
Note on AB6: Line Management PM
Note on AB7: Line Management PM
Note on AO7: System req. Specification OR Market req. Specification is mandatory for safety projets.
Note on AB8: Line Management PM
Note on AO8: System req. Specification OR Market req. Specification is mandatory for safety projets.
Note on A19: Description of functions.
Note on T34: Consulted when hardware relating
Note on U34: Consulted when hardware relating
Note on T35: Consulted when hardware relating
Note on L37: Product Architect is only C if there is any architecture modelling, otherwise I.
Note on T37: Consulted when hardware relating
Note on U37: Consulted when hardware relating
Note on L38: Product Architect is only C if there is any architecture modelling, otherwise I.
Note on L39: Product Architect is only C if there is any architecture modelling, otherwise I.
Note on U39: Consulted when hardware relating
Note on AB50: Also approved by certifying body
Note on AC50: Also approved by certifying body
Note on AD50: Also approved by certifying body
Note on AB51: Also approved by certifying body
Note on AC51: Also approved by certifying body
Note on AD51: Also approved by certifying body
Note on T52: Consulted when hardware relating
Note on U52: Consulted when hardware relating
Note on AL53: Approval at G2 and G5.
Note on T55: Consulted when hardware relating
Note on Q63: For security related test this should be C
Note on A66: When created as a test description
Note on A67: When used as a test record.
Note on Q74: For security related test this should be C
Note on D81: Only for FTT Traceability Report
Note on AA81: Only for PTT Req. Mapping.
Note on AL90: Shall be approved before formal SVT starts.
Note on AB93: Quality Plan
Note on AC93: Quality Plan
Note on AD93: Quality Plan
Note on AI93: Q&Safety Plan
Note on AP93: Use Q&Safety Plan template
Note on Z97: For system the SystemPLM to approve.
Note on Z98: For system the SystemPLM to approve.
Note on O99: Either SW or HW analyst.
Note on P99: Either SW or HW analyst.
Note on AL99: A safety tool selection report shall be approved before using a new or updated tool.
Note on A113: Also used for CC ( Certified Correction).
Note on AL113: Approved at every gate and at the end when all actions are ready.

## Names on RACI
Worksheet: Names on RACI
ROLE | Abbreviations | Project specific sub role | NAME | EMAIL | Org. | Comment
STECO |  |  | Christer Gerding | christer.gerding@se.abb.com | SE
STECO |  |  | Andreas Bäckman | andreas.backman@se.abb.com | SE
STECO |  |  | Per-Arne Redberger | per-arne.redberger@se.abb.com | SE
STECO |  |  | Hans Nordström | hans.b.nordstrom@se.abb.com | SE
STECO |  |  | Thomas Thelin | thomas.thelin@se.abb.com | SE
STECO |  |  | Ralf Jeske | ralf.jeske@de.abb.com | DE
STECO |  |  | Thomas Wiklund | thomas.b.wiklund@se.abb.com | SE
STECO |  |  | Michael Gienke | michael.gienke@de.abb.com | DE
Product Manager | PM | Product Manager 800xA Safety | Per-Arne Redberger | per-arne.redberger@se.abb.com | SE
Product Manager | PM | Product Manager 800xA Engineering | Ralf Jeske | ralf.jeske@de.abb.com | DE
Product Manager | PM | Product Manager 800xA Control | Thomas Thelin | thomas.thelin@se.abb.com | SE
Product Manager | PM | Product Manager S100 | Thomas Wiklund | thomas.b.wiklund@se.abb.com | SE
Technical Product Manager | TPM | PO AC 800M Control IT SW | Rickard Trulsson | rickard.trulsson@se.abb.com | SE
Technical Coordinator (Product Owner) | TC (PO) | PO AC 800M Control IT SW | Håkan Gustavsson | hakan.j.gustavsson@se.abb.com | SE
Technical Coordinator (Product Owner) | TC (PO) | PO CI853 CI854, CI855, CI856, CI857, CI858, CI862, CI865, CI967, CI872, CI873 | Yogesh Alawani | yogesh.alawani@in.abb.com | IN
Technical Coordinator (Product Owner) | TC (PO) | PO CI868 IEC61850 | Karthik V. Padmanaban | karthik.v.padmanaban@in.abb.com | IN
Technical Coordinator (Product Owner) | TC (PO) | PO CI871 Profinet & CI860 FF | Holger Grosse | holger.grosse@de.abb.com | DE
Technical Coordinator (Product Owner) | TC (PO) | PO CI874 OPC UA | Ganesh Rao | ganesh.rao@de.abb.com | DE
Project Manager | PJM |  | Daniel Ardy | daniel.ardy@se.abb.com | SE
Configuration Manager | CM |  | Sven Holmqvist | sven.holmqvist@se.abb.com | SE
Test Responsible | TR |  | Daniel Ardy | daniel.ardy@se.abb.com | SE
Cyber Security Engineer | CSE |  | Yogesh Alawani | yogesh.alawani@in.abb.com | IN
Cyber Security Engineer | CSE |  | Venkata Ravikumar | venkata.a.ravikumar@in.abb.com | IN
Quality Engineer | QE |  | Maria Björkman | maria.bjorkman@se.abb.com | SE | Consultant
Quality Engineer | QE | QE Protocol Bangalore | Srinivas Chakravarthy | srinivas.chakravarthy@in.abb.com | IN
QA Person; CFA Project | QA-person |  | Nicolas Martin-Vivaldi | nicolas.martin-vivaldi@se.abb.com | SE | Consultant
SA Person; CFA Project | SA-person |  | Nicolas Martin-Vivaldi | nicolas.martin-vivaldi@se.abb.com | SE | Consultant
Safety Engineer | SE | Main SE | Fredrik Rosdahl | fredrik.rosdahl@se.abb.com | SE
Safety Engineer | SE |  | Chengyu Huang | chengyu.huang@cn.abb.com | CN
Safety Engineer | SE |  | Harshitha Chandramouli | harshitha.chandramouli@de.abb.com | DE
Safety Engineer | SE |  | Josefin Henriksen | josefin.henriksen@se.abb.com | SE
Safety Engineer | SE |  | Stuart Shirran | stuart.shirran@se.abb.com | SE
EX Representative | ExR |  | Ralf Schaeffer | ralf.schaeffer@de.abb.com | DE
EX Component Responsible | ExCR |  | Ralf Schaeffer | ralf.schaeffer@de.abb.com | DE
User Doc. Skribenta Team Lead |  |  | Harri Parkkonen | harri.parkkonen@se.abb.com | SE
PJM; STT | PJM |  | Neelakandan P. S | neelakandan.p.s@in.abb.com | IN
PJM; S100CI871 | PJM | Delivering S100CI871HwLib | Jacky-JiaQi Wang | jacky-jiaqi.wang@cn.abb.com | CN
PJM; Endurance PM | PJM | Delivering PM86x HW | Louise Fridholm | louise.fridholm@se.abb.com; | SE
PJM; Endurance CI | PJM | Delivering CI8xx HW | Magdalena Forsberg | magdalena.forsberg@se.abb.com | SE
Productization |  |  | Per-Arne Redberger | per-arne.redberger@se.abb.com | SE
Product Architect |  |  | Staffan Andersson | staffan.i.andersson@se.abb.com | SE
Team/Subproject Leaders |  | Scrum Master Team Test | Anders Levin | anders.levin@se.abb.com | SE
Team/Subproject Leaders |  | Scrum Master Team Test Bangalore | Rujuta Ramdurg | rujuta.ramdurg@in.abb.com | IN
Team/Subproject Leaders |  | Scrum Master Team Omega | Martin Isaksson | martin.isaksson@se.abb.com | PAPCP/RCO
Team/Subproject Leaders |  | Team Architect Omega | Johan Olsson | johan.olsson@se.abb.com | PAPCP/RCO
Team/Subproject Leaders |  | Scrum Master Team IOC | Mathias Eng | mathias.eng@se.abb.com | PAPCP/RCO
Team/Subproject Leaders |  | Team Architect Team IOC | Alfred Theorin | alfred.theorin@se.abb.com | PAPCP/RCO
Team/Subproject Leaders |  | Scrum Master Team SM | Mats Rågberger | mats.ragberger@se.abb.com | PAPCP/RES
Team/Subproject Leaders |  | Team Architect Team SM | Olof Holmgren | olof.holmgren@se.abb.com | PAPCP/RES
Team/Subproject Leaders |  | Scrum Master Team Compile | Christina Persson | christina.l.persson@se.abb.com | PAPCP/RCS
Team/Subproject Leaders |  | Team Architect Team Compile | Stefan Sällberg | stefan.sallberg@se.abb.com | PAPCP/RCS
Team/Subproject Leaders |  | Scrum Master Team Aspect & OPC | Joakim Welin | joakim.welin@se.abb.com | PAPCP/RCS
Team/Subproject Leaders |  | Team Architect Team Aspect & OPC | Niklas Giheden | niklas.giheden@se.abb.com | PAPCP/RCS
Team/Subproject Leaders |  | Scrum Master Team GUI | Peter Palvén | peter.palven@se.abb.com | PAPCP/RCS
Team/Subproject Leaders |  | Team Architect Team GUI | Ulf Andersson | ulf.s.andersson@se.abb.com | PAPCP/RCS
Team/Subproject Leaders |  | Build & Installation | Sven-Åke Nord | sven-ake.nord@se.abb.com | PAPCP/RCB
Team/Subproject Leaders |  | PROFINET CI871 and FF CI860 | Olaf Schmidt | olaf.schmidt@de.abb.com | R&D-DE-SW
Team/Subproject Leaders |  | Scrum Master Team Control Maintenance, Bangalore | Srikanth Parthasarathy | parthasarathy.srikanth@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team Omega | Peter Nilsson | peter.l.nilsson@se.abb.com | PAPCP/RCO
Team/Project Members |  | Team Omega | Michael Nordström | michael.nordstrom@se.abb.com | PAPCP/RCO
Team/Project Members |  | Team Omega | Douglas Beniz | douglas.beniz@se.abb.com | PAPCP/RCO
Team/Project Members |  | Team Omega | Johan Persson | <not available yet> | PAPCP/RCO | Started 2022-09-05
Team/Project Members |  | Team IOC | Anna Andgart | anna.andgart@se.abb.com | PAPCP/RCO
Team/Project Members |  | Team IOC | Martin Andersson | martin.andersson@se.abb.com | PAPCP/RCO
Team/Project Members |  | Team IOC | Magnus Jonasson | magnus.h.jonasson@se.abb.com | PAPCP/RCO
Team/Project Members |  | Team IOC | Anders Tilly | anders.tilly@se.abb.com | PAPCP/RCO
Team/Project Members |  | Team IOC | Thomas Fay | thomas.fay@se.abb.com | PAPCP/RCO | Started 2022-10-04
Team/Project Members |  | Team SM | Mattias Willén | mattias.willen@se.abb.com | PAPCP/RES
Team/Project Members |  | Team SM | Thomas Karlsson | thomas.z.karlsson@se.abb.com | PAPCP/RES
Team/Project Members |  | Team SM | Robert Kostelac | robert.kostelac@s.abb.com | PAPCP/RES
Team/Project Members |  | Team SM | Bjarne Johansson | bjarne.johansson@se.abb.com | PAPCP/RES
Team/Project Members |  | Team Compile | Fredrik Matsson | fredrik.matsson@se.abb.com | PAPCP/RCS
Team/Project Members |  | Team Compile | Elin Kristensson | elin.kristensson@se.abb.com | PAPCP/RCS
Team/Project Members |  | Team Compile | Sumit Shinde | sumit.shinde@se.abb.com | PAPCP/RCS
Team/Project Members |  | Team Compile | Marco Vittori | marco.vittori@se.abb.com | PAPCP/RCS | Started 2022-06-07
Team/Project Members |  | Team Aspect & OPC | Anders Karlsson | anders.x.karlsson@se.abb.com | PAPCP/RCS
Team/Project Members |  | Team Aspect & OPC | Magnus Rydqvist | magnus.rydqvist@se.abb.com | PAPCP/RCS
Team/Project Members |  | Team GUI | Andreas Thilderqvist | andreas.thilderqvist@se.abb.com | PAPCP/RCS
Team/Project Members |  | Team GUI | Håkan Augustsson | hakan.augustsson@se.abb.com | PAPCP/RCS
Team/Project Members |  | Team GUI | Nebojsa Dacevic | nebojsa.dacevic@se.abb.com | PAPCP/RCS | Started 2022-06-16
Team/Project Members |  | Team PROFINET CI871 | Werner Bregulla | werner.bregulla@de.abb.com | R&D-DE-SW
Team/Project Members |  | Team PROFINET CI871 | Rafael Selent | rafael.selent@de.abb.com | R&D-DE-SW
Team/Project Members |  | Team PROFINET CI871 | Dirk Dietrich | dirk.dietrich@de.abb.com | R&D-DE-SW
Team/Project Members |  | Team FF CI860 | Werner Bregulla | werner.bregulla@de.abb.com | R&D-DE-SW
Team/Project Members |  | Team FF CI860 | Marten Hinrichs | marten.hinrichs@de.abb.com | R&D-DE-SW
Team/Project Members |  | Team S100 | Akhilesh Patel | akhilesh.patel@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team S100 | Venkata Ravikumar | venkata.a.ravikumar@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team Modbus TCP | Vignesh R | vignesh.r@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team Modbus TCP | Girish Nadig | girish.nadig@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team Modbus TCP | Raghavendra H | raghavendra.h@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team Profibus DIW | Srikanth Kv | srikanth.kv@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team Profibus DIW | Indupriya | indupriya.c@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team EtherNetIP DIW | Pavan ML | pavan.ml@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team EtherNetIP DIW | Indupriya | indupriya.c@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team EtherNetIP CI873 s200IoCI873Hwlib | Ashwini Chandra | ashwini.chandra@in.abb.com | IDC/PAPCP | Consultant
Team/Project Members |  | Team EtherNetIP CI873 s200IoCI873Hwlib | Naveen K | naveen.k@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team EtherNetIP CI873 s200IoCI873Hwlib | Vignesh R | vignesh.r@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team EtherNetIP CI873 s200IoCI873Hwlib | Venkata Ravikumar | venkata.a.ravikumar@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team SattIO CI865 | Venkata Ravikumar | venkata.a.ravikumar@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team MB300 CI855 | Naveen K | naveen.k@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team MB300 CI855 | Akhilesh Patel | akhilesh.patel@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team MB300 CI855 | Vinod Pradhan | vinod.pradhan@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team Modbus RTU | Girish Nadig | girish.nadig@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team Modbus RTU | Raghavendra H | raghavendra.h@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team S3964 | Vinod Pradhan | vinod.pradhan@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team S3964 | Akhilesh Patel | akhilesh.patel@in.abb.com | IDC/PAPCP
Team/Project Members |  | TeamProfibus CI854A/B FpbaCI854Hwlib | Naveen K | naveen.k@in.abb.com | IDC/PAPCP
Team/Project Members |  | TeamProfibus CI854A/B FpbaCI854Hwlib | Vinod Pradhan | vinod.pradhan@in.abb.com | IDC/PAPCP
Team/Project Members |  | TeamProfibus CI854A/B FpbaCI854Hwlib | Deep Anand | deep.anand@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team COMLI | Venkata Ravikumar | venkata.a.ravikumar@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team TRIO CI862 | Akhilesh Patel | akhilesh.patel@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team INSUM CI857 | Naveen K | naveen.k@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team INSUM CI857 | Venkata Ravikumar | venkata.a.ravikumar@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team MOD5 CI872 | Venkata Ravikumar | venkata.a.ravikumar@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team MOD5 CI872 | Akhilesh Patel | akhilesh.patel@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team IEC 61850 DIW | Pavan ML | pavan.ml@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team IEC 61850 DIW | Srikanth Kv | srikanth.kv@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team IEC 61850 CI868 | Deep Anand | deep.anand@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team IEC 61850 CI868 | Akhilesh Patel | akhilesh.patel@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team DRIVEBUS CI858 | Akhilesh Patel | akhilesh.patel@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team DRIVEBUS CI858 | Naveen K | naveen.k@in.abb.com | IDC/PAPCP
Team/Project Members |  | Technical Manager Development | Girish Nadig | girish.nadig@in.abb.com | IDC/PAPCP
Team/Project Members |  | Technical Manager Development | Venkata Ravikumar | venkata.a.ravikumar@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team PTT/SVT Malmö | Pär Eklund | par.eklund@se.abb.com | PAPCP/RCB
Team/Project Members |  | Team PTT/SVT Malmö | Erik Axelsson | erik.axelsson@se.abb.com | PAPCP/RCB
Team/Project Members |  | Team PTT/SVT Malmö | Mikael Lund | mikael.lund@se.abb.com | PAPCP/RCB
Team/Project Members |  | Team PTT/SVT Malmö | Harald Svensson | harald.svensson@se.abb.com | PAPCP/RCB | Consultant
Team/Project Members |  | Team PTT/SVT Malmö | Adam Barjosef | adam.barjosef@se.abb.com | PAPCP/RCB | Consultant
Team/Project Members |  | Team PTT/SVT Malmö | Olle Persson | olle.persson@se.abb.com | PAPCP/RCB | Consultant
Team/Project Members |  | Team PTT/SVT Malmö | Lars Heinegård | lars.heinegard@se.abb.com | PAPCP/RCB | Consultant
Team/Project Members |  | Team PTT/SVT Malmö | Chithanh Mach | chithanh.mach@se.abb.com | PAPCP/RCB | Consultant
Team/Project Members |  | Team PTT/SVT Malmö | Sarah Borg | sarah.borg@se.abb.com | PAPCP/RCB | Consultant
Team/Project Members |  | Team PTT Bangalore | Channana Gouda | channana.gouda@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team PTT Bangalore | Thirumalai M | thirumalai.m@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team PTT Bangalore | Sai Chaitanya | sai.chaitanya@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team PTT Bangalore | Madhavkrishnan.P | madhavkrishnan.p@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team PTT Bangalore | Gyson George | gyson.pgeorge@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team PTT Bangalore | Sandeep R | sandeep.r1@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team PTT Bangalore | Atul Jadhav | atul.baliramjadhav@in.abb.com | IDC/PAPCP
Team/Project Members |  | Team PTT Bangalore | Anu Cherian | anu.cherian@in.abb.com | IDC/PAPCP | Consultant
Team/Project Members |  | Team PTT Bangalore | Sourabh Jaiswal | saurabh.jaiswal@in.abb.com | IDC/PAPCP | Consultant
Team/Project Members |  | Team PTT Bangalore | Venkategowda IR | venkategowda.ir@in.abb.com | IDC/PAPCP | Consultant
Team/Project Members |  | Team PTT Bangalore | Mahantesh Patil | mahantesh.patil@in.abb.com | IDC/PAPCP | Consultant
Team/Project Members |  | Team PTT Bangalore | Channabasava D | channabasava.d@in.abb.com | IDC/PAPCP | Consultant
Team/Project Members |  | Team PTT Bangalore | Roopa Benakalli | roopa.benakalli@in.abb.com | IDC/PAPCP | Consultant
Team/Project Members |  | Team PTT Bangalore | VenkatRajshekhar Patina | venkatarajasekhar.patina@in.abb.com | IDC/PAPCP | Consultant
Software analyst |  |  | Håkan Gustavsson | hakan.j.gustavsson@se.abb.com | SE
Hardware analyst |  |  | Martin Rydberg | martin.rydberg@se.abb.com | SE
System Architect |  |  | Staffan Andersson | staffan.i.andersson@se.abb.com | SE
Line Management TPM | LM TPM |  | Christer Gerding | christer.gerding@se.abb.com | SE
Line Management R&D | LM R&D | Line Manager Protocol Bangalore | Arun Babu | arun.babu@in.abb.com | IN
Line Management R&D | LM R&D |  | Christer Gerding | christer.gerding@se.abb.com | SE
Line Management R&D | LM R&D |  | Mårten Svensson | marten.svensson@se.abb.com | SE
Line Management R&D | LM R&D |  | Michael Gienke | michael.gienke@de.abb.com | DE
Line Management Quality | LM Q |  | Tomasz Halajda | tomasz.halajda@de.abb.com | DE
LM; STT | LM STT |  | Dhaval Mehta | dhaval.mehta@in.abb.com | IN
LM; SupportLine | LM SL3 |  | Tore Lundholm | tore.lundholm@se.abb.com | SE
LM; Sales and Market Communication | LM |  | Johan Björklund | johan.bjorklund@ch.abb.com | CH
Head of Cyber Security |  |  | Tomas Lindström | tomas.lindstrom@se.abb.com | SE
Functional Safety Manager (safety) | FSM |  | Tomasz Halajda | tomasz.halajda@de.abb.com | DE
Note on E3: If you have sub roles for the different roles in RACI, add a line and add the sub role name.
Note on I3: This column can be used to indicate a suitable reoplacement should the usual named individual be unavailable, e.g. for delegation of meeting invitations or during periods of absence. The delegate/alternate(s) must also be listed in the "Names on RACI" worksheet so that their contact details are known.

## Invite example - RACI
Worksheet: Invite example - RACI
Recommended content for a Review invitation using RACI.
Invitees to formal reviews of a deliverable shall follow the RACI content and roles. For informal reviews the format and participants of the invitation are open and can be chosen as the review organiser best sees fit.
""
Dear Colleague,
If you are on the list below, you are listed as Consulted in the Names on RACI and expected to participate in the review of:
Document:
"xx" <link to Document Management System>
This review is intended for Release of <CIT 5.1>.
If you have a consulted RACI role it is mandatory for you to review the document and give your comments.
You are expected to accept or decline at latest the day before the meeting.
Written comments or a notice of no comments are expected if you will not attend the meeting but are listed as to be consulted.
SIL Level:
x <None, 1, 2 or 3>
Assigned meeting roles: Nominated:
Author(s): x
Chairman: x
Secretary: x
Consulted: RACI Roles: View Points:
x STECO xxx
x Project Manager xxx
x Technical Coordinator xxx
x Configuration Manager xxx
x Test Responsible xxx
x PJM; STT
x Productization
x Product Architect
x Team/Subproject Leaders
x Team/Project Members
x Software Analyst
x Hardware Analyst
x Cyber Security Engineer
x Quality Engineer
x Safety Engineer
x EX Representative
x EX Component Responsible
x QA Person; CFA Project
x SA Person; CFA Project
x System Architect
x Skribenta User Doc. Team Lead
x Product Manager
x Technical Product Manager
x Line Management R&D
x LM; STT
x LM; SupportLine
x LM; sales and market communication
x Head of Cyber Security
x Functional Safety Manager (safety)
x -
Call in Number:
<+46 08 xxxxxxxxx>
- It is your obligation as reviewer to notify the chairman before the review if you think the document is not ready for review.
- Every applicable viewpoint above is expected to be represented by at least one Consulted reviewer during the meeting either by participation or by written comments.
- For other invitees (Informed or Accountable) it is optional to attend the meeting and send written comments.
- The main purpose of the review is to gather comments and opinions about the document from participants. No detailed technical issues will be handled during the meeting. If the technical content of the document is likely to cause debate then an informal review ahead of the formal review to resolve this detail is better.
- Written comments and participation notification should be sent to the chairman no later than the day before the meeting. It is recommended that comments are in English and written in a form that can be added directly to the Review Record. For simplicity using a blank RR template in Excel is often easier and faster than adding comments to the actual 3BSExxxxxx-RR associated with the document.
Best regards,
<name of Responsible>
""

## Invite example - Viewpoints
Worksheet: Invite example - Viewpoints
Recommended content for a Review invitation using Viewpoints.
Invitees to formal reviews of a deliverable can, for a limited set of documents, follow the Roles - Viewpoints worksheet content and roles. All participants marked in RACI still needs to be invited but not all are given a viewpoint role. For informal reviews the format and participants of the invitation are open and can be chosen as the review organiser best sees fit.
""
Dear Colleague,
If you are on the list below, you have a role marked in the Names on RACI (Roles-Viewpoints worksheet) and expected to participate in the review of:
Document:
"xx" <link to Document Management System>
This review is intended for Release of <CIT 5.1>.
Expected participants are given viewpoints from which perspective their roles shall review the document. (Viewpoint-description see 3BSE039313)
If you have been assigned to a viewpoint it is mandatory for you to review the document and give your comments.
You are expected to accept or decline at latest the day before the meeting.
Written comments or a notice of no comments are expected if you will not attend the meeting but are assigned to a viewpoint.
SIL Level:
x <None, 1, 2 or 3>
Assigned meeting roles: Nominated:
Author(s): x
Chairman: x
Secretary: x
Consulted: View Points:
x Formalities
x Traceability
x Functional user
x Architecture
x Architecture/UML
x Safety
x DTD Safety
x Different
x Security
x Testability
x Realization
x Test Quality
x Test Coverage
x Technical Correctness
x Ex certification conformity
x Ex design conformity
Call in Number:
<+46 08 xxxxxxxxx>
- It is your obligation as reviewer to notify the chairman before the review if you think the document is not ready for review.
- Every applicable viewpoint above is expected to be represented by one assigned reviewer during the meeting either by participation or by written comments.
- For other invitees (Informed or Accountable) it is optional to attend the meeting and send written comments.
- The main purpose of the review is to gather comments and opinions about the document from participants. No detailed technical issues will be handled during the meeting. If the technical content of the document is likely to cause debate then an informal review ahead of the formal review to resolve this detail is better.
- Written comments and participation notification should be sent to the chairman no later than the day before the meeting. It is recommended that comments are in English and written in a form that can be added directly to the Review Record. For simplicity using a blank RR template in Excel is often easier and faster than adding comments to the actual 3BSExxxxxx-RR associated with the document.
Best regards,
<name of Responsible>
""

## Roles - Viewpoints
Worksheet: Roles - Viewpoints
Viewpoints is an alternative method to use for the documents listed in the columns below and is intended to be a help in finding the right persons to invite for a review. This worksheet provides help to find a suitable person for the different viewpoints for a review. All roles marked in the RACI chart shall be invited to the review and given the opportunity to make remarks on the document. The inviter shall also assign one of the marked persons in this worksheet to each viewpoint and that person is responsible of reviewing the document with focus on this area. It is mandatory for a person who has been assigned to a viewpoint to participate or send written comments. CH=consulted when Hardware relating
DoF | IfD | DD | PTTD | FTTD | DTD | Viewpoint | STECO | Project Manager | Technical Coordinator | Configuration Manager | Test Responsible | PJM; STT | Productization | PJM; documentation | Product Architect | Team/Subproject Leaders | Team/Project Members | Software analyst | Hardware analyst | Cyber Security Engineer | Quality Engineer | Safety Engineer | EX Representative | EX Component Responsible | QA; CFA Project | SA; CFA Project | System Architect | Technical writer | Product Manager | Technical Product Manager | Line Management R&D | LM; STT | LM; SupportLine | LM; sales and market communication | Head of Cyber Security | Functional Safety Manager (safety)
x | x | x | x | x | x | Formalities |  | x | [7 empty] | x | x |  |  |  | x
x | x | x | x | x | x | Traceability |  | x | [7 empty] | x | x
x | [5 empty] | Functional user | [22 empty] | x | x
x | [5 empty] | Architecture |  |  | x | [5 empty] | x
| x | x |  |  |  | Architecture/UML |  |  | x | [5 empty] | x |  | x
x | x | x | x | x |  | Safety | [15 empty] | x
[5 empty] | x | DTD Safety | [10 empty] | x |  |  |  |  | x
x | [5 empty] | Different |  |  | x | [12 empty] | x
x | x | x |  |  |  | Security | [13 empty] | x | [14 empty] | x
x |  | x |  |  |  | Testability |  |  |  |  | x | [5 empty] | x
x | x | x |  |  |  | Realization | [10 empty] | x | [12 empty] | x
|  |  | x | x | x | Test Quality | [10 empty] | x | [12 empty] | x
|  |  | x | x | x | Test Coverage |  | x |  |  | x | [5 empty] | x
|  |  | x |  |  | Technical Correctness | [10 empty] | x | [12 empty] | x
x | [5 empty] | Ex certification conformity (CH) | [16 empty] | x
x |  | x | x | x |  | Ex design conformity (CH) | [17 empty] | x
Note on A3: Not valid for 1131 Libraries
Note on W3: Mandatory for safety development only
Note on G9: Mandatory for safety development only
Note on G10: Mandatory for safety development only
Note on G11: Mandatory for safety development only.

## Guidance - Viewpoints
Worksheet: Guidance - Viewpoints
Guidance Viewpoints
The following is to be used as a guidance on what to keep in focus when reviewing a document from a viewpoint perspective. When reviewing outgoing from a viewpoint, the checklist (3BSE028024 Checklist for Reviews) for the reviewed document shall be used together with this guidance. The checklists contains information on specific items to check based on each viewpoint. A reviewer is always free to give comments from other perspectives than the assigned viewpoint.
All Document types
Formalities
  Correct template used
  Invitation List according to RACI or Viewpoint
  All chapters filled in or marked N/A.
  PRC present for the change with right target product release and mentioned in revision history?
  General impression of the document
Description of Function (DoF) (Not valid for 1131 Libraries)
Traceability
  Is it described how the requirements of the described functions are realized?
  Are non-functional requirements fulfilled?
  (For more information about traceability for DoF see 3BSE067721 ABB approach to IEC61508, Traceability)
Functional user
  Will the customer be satisfied?
  Is the function user friendly?
Architecture
  Connection to architecture documents
  Is the functions correctly modeled using UML?
Safety
  Any possible safety issues in the described functions?
  Is the 3BSE038862 Safety Handbook followed?
  Is SIL-level correct and is it clearly indicated?
Different
  Is ABB approach to avoid common cause failure followed?
  If it's a function in both PM and SM is 3BSE045438 ABB Approach to avoid common cause failure updated
Security
  Any possible security issues in the described functions?
Testability
  Is testing considered in the functional design?
Realization
  Is the functionality described clear enough to go on with DD and implementation?
Ex design conformity (CH)
  Is the design conform according to the required Ex type of protection?
  Are the needed functions for Ex considered and clearly indicated?
Ex certification conformity (CH)
  Reflects the concept of design the defined Ex architecture and are the current standards applied?
  Are the Ex quality requirements considered and followed at development and handover of documents to manufacturers?
  Are the right Ex types of protection used, that it can be produced at manufacturers?
Interface Description (IfD)
Traceability
  Is it described how the requirements of the described interfaces are realized?
  Are non-functional requirements fulfilled?
  (For more information about traceability for IfD see 3BSE067721 ABB approach to IEC61508, Traceability )
Architecture/UML
  Are the interfaces modeled on the right level of the architecture?
  Are complex interface operations modeled correctly using UML?
Safety
Any possible safety issues in the described functions?
Is the 3BSE038862 Safety Handbook followed?
Is SIL-level correct and is it clearly indicated?
Realization
  Is the interface described clear enough to go on with DD and implementation?
Security
  Any possible security issues in the described interfaces?
Design Description (DD)
Traceability
  Is it described how the DoF functions are realized?
  Are non-functional requirements fulfilled?
  (For more information about traceability for DD see 3BSE067721 ABB approach to IEC61508, Traceability )
Architecture/UML
  Are the subsystems/modules placed in the correct model?
  Are complex operations modeled correctly using UML?
Safety
Any possible safety issues in the described functions?
Is the 3BSE038862 Safety Handbook followed?
Is SIL-level correct and is it clearly indicated?
Security
  Any possible security issues in the described functions?
Testability
  Is testing considered in the design?
Realization
  Is the design good enough to continue with code implementation?
Ex design conformity (CH)
  Is the design conform according to the required Ex type of protection?
  Are the needed functions for Ex considered and clearly described?
  Are the Ex rules considered at calculations (Eg. : tolerances and safety factors)?
Product Type Test Description (PTTD)
Traceability
  Check that the table of requirements is correct (all requirements present, test cases for every requirement)
  (For more information about traceability for PTTD see 3BSE067721 ABB approach to IEC61508, Traceability)
Safety
Is SIL-level correct and is it clearly indicated?
Is the 3BSE038862 Safety Handbook followed?
Test Quality
  Is there a purpose for every test case?
  Are preparations and executions described in a clear enough way for a not initiated person to do the test?
  Are there expected results described for each test case and are they described on a suitable level?
Test coverage
  Are the test cases "realistic", do they imitate realistic situations?
  Are there test cases for extreme situations?
  Are there tests for user friendliness?
Technical correctness
  Is the description of how to perform the tests and the expected result technically correct?
Ex design conformity (CH)
  How are Ex related requirements of a component confirmed and documented?
  What documents will be referenced to confirm Ex related requirements?
  How will be requirements covered, which are defined as "Non-verified"?
Function or Component Type Test Description (FTTD/CTTD) (Not valid for 1131 Libraries)
Traceability
  Traceability to functions in the input DoFs?
  (For more information about traceability for FTTD/CTTD see 3BSE067721 ABB approach to IEC61508, Traceability)
Safety
  For tests where code is executed in the controller, the code shall be downloaded and not just simulated
  Is SIL-level correct and is it clearly indicated?
  Is the 3BSE038862 Safety Handbook followed?
Test coverage
  Are there test cases for all use cases? (basic and alternative flows)
Test Quality
  Is the general impression of the test cases that they are well written and understandable?
  Are all information needed to be able to run and reproduce the tests?
Ex design conformity (CH)
  Are the required Ex related dynamic evidences defined?
  E.g.: Oscilloscope shoot for fast switch off for intrinsically circuits?
  What are the dynamic behavior of signals and what power will be dissipated (SOA)?
  Are the right tests to evaluate the efficiency characteristic of DC/DC converters defined?
  Are the right tests to evaluate inductive and capacitive loads defined?
  Note: Not all required Ex tests will be made under eyewitness or are part of the Ex examination documents.
Design Test Description (DTD)
Traceability
  Traceability to DD and definition files?
  (For more information about traceability for DTD see 3BSE067721 ABB approach to IEC61508, Traceability)
DTD Safety
Is the 3BSE038862 Safety Handbook followed?
  Is SIL-level correct and is it clearly indicated?
Test coverage
  Check that all methods are present and that there are test cases for the public methods
  Code coverage according to 3BSE039245 ABB approach to IEC61508 2nd Ed, Test?
Test Quality
  Is the general impression of the test cases that they are well written and understandable?

## adm (hidden)
Worksheet: adm
Ptype | Gate
All projects | G0
Development | G1
Rollups | G2
Temp. Correction | G3
System | G4
STT | G5
HW | G6
SW
Safety
Title

## Template Revision history (hidden)
Skeleton history
Revision | Sheet (S) Row (R) | Description | Date Dept./Name
-d1 | All | New document from Pluto-0013 and 3BSE025114 | 2004-01-11 ATPA/XA/ACD Tina Klang
-d2 |  | Updated before review | 2005-01-28 ATPA/XA/ACD Tina Klang
-d3 |  | Mainly structure changes in the document | 2005-02-21 ATPA/XA/ACP Bengt Larsson
-d4 |  | Updates after second formal review | 2005-03-03 ATPA/XA/ACD Tina Klang
- |  | Checked after review and sent for approval. Replace 3BSE025114 App A | 2005-03-04 ATPA/XA/ACP Bengt Larsson
Ad1 |  | Several updated | 2005-09-13 ATPA/XA/ACP Tina Klang
Ad2 |  | Updates after review | 2005-09-27 ATPA/XA/ACP Tina Klang
Ad3 |  | Changes after review | 2005-09-27 ATPA/XA/ACP Tina Klang
A | No changes | The document is ready for approval | 2005-09-30 ATPA/XA/ACP Harriet Lindgren Larsson
Bd1 |  | Small updates | 2005-10-28 ATPA/XA/ACP Tina Klang
Bd3 |  | Updates after formal review | 2005-12-05 ATPA/XA/ACP Tina Klang
B | No changes | Ready for approval | 2005-12-21 ATPA/XA/ACP Tina Klang
Cd2 |  | Deleted Test Summary. This is included in Summary for Final Conclusion of test. Change name "Final Conclusion of test" to " Summary for Final Conclusion of test" Removed C on "Product Manager" for document "Interface Description", changed G3 to G4. | 2006-03-02 ATPA/XA/ACP Tina Klang
Cd3 | All | Updated after review | 2006-04-03 PA/XA/AOT Katarina Abremark
C | No changes | The document is ready for approval | 2006-05-24 PA/XA/ACP Harriet Lindgren Larsson
Dd1 | Row: Software HAZOP Report. Column: Formal Review Record. | Changed according to Tracker Control IT Documents #486. Removed Formal Review Record requirement for Software HAZOP Report. | 2006-12-13 PA/XA/ACT Thomas Thelin
D | No changes | The document is ready for approval | 2006-12-19 PA/XA/ACT Thomas Thelin
Ed1 | New column and row | Added column for LM Product development System and added a row for System requirements spec. | 2007-04-04 PA/XA/AOP Katarina Porath
Ed2 |  | Added colour for changes made earlier to highlight changes for review | 2007-06-12 PA/XA/AOP Katarina Porath
Ed3 |  | Removed Highlighted colour from Product Bulletin. | 2007-06-27 PA/XA/AOP Katarina Porath
Ed4 | New column | Added column for Process owner | 2007-08-23 PA/XA/AOP Katarina Porath
Ed5 | New row | Added System software version, removed Product Bulletin | 2007-08-27 PA/XA/AOP Katarina Porath
Ed6 | All | Updated according to RR | 2007-10-02 PA/XA/AOP Katarina Porath
Ed7 | Cell comments | Added macro to enlarge cell comments when clicking in the cell | 2007-10-02 PA/XA/AOP Katarina Porath
E |  | Ready for approval | 2007-10-16 PA/XA/AOP Katarina Porath
F |  | Ready for approval. Changed that Integration Plan shall be approved at G2. Informally reviewed by Katarina Porath and Christer Persson. | 2007-10-22 PA/XA/AOP Katarina Porath
G |  | Ready for approval. TTPs (PTT & STT) approval gate changed from G4 to G3. Informally approved 2008-04-30 by the V&V team (see V&V meeting list). Changes checked by Christer Persson. | 2008-04-30 PA/XA/AOP Michael Wahlberg
Hd1 | New row | Added new row: Troubleshooting Guide , TSG | 2009-01-09 PA/XA/AOP Mats Ohlsson
Hd2 | All | Updated according to RR | 2009-08-13 PAPR/XAAO Christer Persson
H |  | Ready for approval. Document type TSG (Trouble Shooting Guide) added. | 2009-08-14 PAPR/XAAO Christer Persson
Id1 | New column (AG) | Added SSAT as review team | 2009-09-30 PAPR/XAAOP Lars Draws
Id2 |  | Updated based on review comments | 2009-10-15 PAPR/XAAOP Lars Draws
I |  | Ready for approval | 2009-10-29 PAPR/XAAOP Lars Draws
Jd1 | All | Update to reflect current organization and organizational needs. | 2010-09-01 PAPR/XAAO Jens Axelsson
Jd2 | All | Removed some unused documents. | 2010-09-24 PAPR/XAAO Jens Axelsson
Jd3 | Added three sheets and some VBA code | Added support for names on RACI. Added support for View Points. Added lotus notes integration. | 2010-10-13 PAPR/XAAO Jens Axelsson
Jd4 | Five new columns and one row | Updated with V&V Checklists in accordance with C2 (2446/2008). | 2010-10-19 PAPR/XAAO Jens Axelsson
Jd5 |  | Updated according to review 2010-10-28 | 2010-10-28 PAPR/XAAO Jens Axelsson
Jd6 |  | Updated according to review 2010-10-28 | 2010-11-04 PAPR/XAAO Jens Axelsson
Jd7 |  | Added C to CTT TD on Team Member | 2010-11-26 PAPR/XAAO Jens Axelsson
Jd8 |  | Updated according to formal review 2010-12-16 | 2010-12-17 PAPR/XAAO Jens Axelsson
Jd9 |  | Updated according to formal review 2011-01-19 | 2011-01-20 PAPR/XAAO Jens Axelsson
J |  | Approved | 2011-03-14 PAPR/XAAO Erik Gynt
K |  | Removed the "invitation builder part" because it didn't work properly | 2012-05-04 PAPR/XAQM Bengt Larsson
Ld0 | Overview, RACI,Help | Added "overview",changed way to show when documents ready, added info about where to find skeletons, new help-sheet. | 2012-07-06 PAPR/XAQ Bengt Larsson
Ld1 | RACI,Overview,adm | added "valid for" as column both in RACI and Overview. Column "Sub project role" added in "Names on RACI", "Adm" added as hidden worksheet | 2012-07-09 PAPR/XAQ Bengt Larsson
Ld2 | Names on RACI, Overview | Added column abbreviations in worksheet "Names on RACI", added documents FCA and PCA and some minor other updates | 2012-07-16 PAPR/XAQ Bengt Larsson
Ld3 | RACI, overview | Removed "several approval" so it now always is one approver at ABB. Changed help text for documents also approved by certifying body. | 2012-09-10 PAPR/XAQ Bengt Larsson
Ld4 | RACI,Overview | Added "safety tool selection report" | 2012-09-11 PAPR/XAQ Bengt Larsson
Ld5 | RACI,Overview | Added "Quality system overview" | 2012-09-28 PAPR/XAQ Bengt Larsson
Ld6 | RACI, overview | Changed SSAT chairman to 800xA System Architecture Responsible | 2012-10-30 PAPR/XAQ Bengt Larsson
Ld7 | RACI, overview | Added responsible for "checklist for SVT" and noted "test responsible" as C for "checklist start of PTT". Added "system product line manager" and noted A for "System RS". Steco noted C for "SystemRS". | 2012-11-06 PAPR/XAQ Bengt Larsson
Ld8 | RACI,overview | Changes according to RR and e.g. documents "product integration milestone" and "user doc. DCP" added | 2012-11-29 PAPR/XAQ Bengt Larsson
Ld9 | RACI,overview | Changed/Added information for "Integration plan", "product integration milestone" and "user doc. DCP". | 2012-12-06 PAPR/XAQ Bengt Larsson
Ld10 | Help,RACI,overview | Updated according to RR. Mainly changed handling around "user doc. DCP" | 2012-12-20 PAPR/XAQ Bengt Larsson
L |  | Ready for approval, (case HP ALM process change management #113) | 2013-01-09 PAPR/XAQ Katarina Porath
Md0 | RACI,overview | Case HP ALM process change management #148, SCC,ITD and FTT Trac. Report added, reference in "help" to viewpoints removed. Change responsible for product guide and system sw versions. SA person "C" for Q&S-plan. IFD changed ready-gates. PM and test resp. "consulted" for MRS;SRS*2 | 2013-03-07 PAPR/XAQ Bengt Larsson
Md1 | RACI,overview | Added participation for Product management after discussion with product manager | 2013-03-11 PAPR/XAQ Bengt Larsson
Md2 | RACI,overview | Add I and C for "LM: sales and …." on documents Product guide and Release notes | 2013-04-05 PAPR/XAQ Bengt Larsson
Md3 | RACI,overview | Changed Test Responsible from "I" to "C" | 2013-04-18 PAPR/XAQ Bengt Larsson
Md4 | RACI, overview | PCR#107, gate info changed for req. traceability matrix | 2013-08-06 PAPR/XAQ Bengt Larsson
Md5 | Help,RACI,overview | Update after formal review | 2013-10-07 PAPR/XAQ Bengt Larsson
Md6 | RACI,overview | Minor editorial changes, added baselines for test review and code review records | 2013-10-29 PAPR/XAQ Bengt Larsson
M |  | Document ready for approval. | 2013-11-01 PAPR/XAAH Ulrika Nilsson
Nd0 |  | Skeleton converted to ABB templates and safety impact added according to PCR #380. | 2014-07-02 PAST/PAOD Marie Granlund
N | - | Skeleton reviewed and approved by Ulrika Nilsson. | 2014-09-12 PAPR/XAAH Ulrika Nilsson
Od1 | RACI, Overview RACI, Names on RACI RACI, Overview RACI RACI, Names on RACI RACI, Overview RACI, Names on RACI | PCR#320 (RACI covers both system and product projects will be deferred again, added DTP.) PCR#378 SE included in Circuit Diagram review, added delegation column, invitation example (role descriptions will be covered by new QMS) PCR#384 missing docs in RACI (3rd party not to be added and export control lists to be discussed). PCR#391 Novo audit inputs (at least one C for non safety projects; aligned naming of temps) (LLITD and DTD test responsible to be I-Informed covered by PRC#431) PCR#419 Updated Requirement Management interactions and roles. PCR#425 TTT-> ABBTemplates. PCR#431 Re-introduced QE role to RACI, updated RACI roles for FTTD/CTTD, FPGA veri. descrip., DTD and LLITD | 2015-01-20 PACT/XAACO Stuart Shirran
Od2 | RACI | Updated after informal review 2015-01-22 | 2015-01-22 PACT/XAACO Stuart Shirran
Od3 |  | Preparation for formal review | 2015-01-29 PACT/XAACO Stuart Shirran
Od4 | Help, Overview, RACI, Invite to review example, Roles-viewpoints | Updated with review comments from 2015-02-05 & 17 | 2015-02-24 PACT/XAACO Stuart Shirran
Od5 | Help, RACI, Roles-viewpoints | Updated with review comments from 2015-03-5 & checked in to ECM. Long delay in checking in due to 5.1 RU3 workload. | 2015-08-10 PACT/XAACO Stuart Shirran
Od6 | Help, RACI, Names on RACI, Roles-viewpoints, Invite to review example | Updated with review comments from "review form 5" and "review form 6" created new worksheet "Invite example - Viewpoints, changed name of worksheet "Invite to review example" to "Invite example - RACI". #454 Added worksheet "Guidance - Viewpoints" | 2015-10-06 PACT/XAAEP Lisa Alm
Od7 | Gen, Help, RACI, Invite example-Viewpoints, Guidance-Viewpoints, Roles-Viewpoints | Added info on guidance-viewpoint worksheet. Updated Guidance-Viewpoints worksheet. Updated RACI worksheet with abbrevations. Updated Roles-Viewpoints roles. General updated every sheet with name of worksheet in top left field. Updated column for QE in RACI worksheet. Changed name of "Detailed Test Plan" to "Test Summary and Final Conclusion of Test (Detailed Test Plan)" to make clear it's the same document as Final CoT | 2015-11-20 PACT/XAAEP Lisa Alm
Od8 | All | Minor updates during change check phase. | 1900-01-00
Od9 | Roles - Viewpoints, Guidance Viewpoints | Minor updates during change check phase. Added "x" to TC again in Roles Viewpoints. Added text "Not valid for 1131 Libraries" for DoF and FTTD in Guidance Viewpoints | 2016-01-04 PACT/XAAEP Lisa Alm
Od10 | RACI, Overview | Removed Product Integration Test Descr & Record (PITD and PITR) according to case #574 | 2016-01-27 PACT/XAAEP Lisa Alm
Od11 | Template Revision | Removed "strikethrough" and added "()" for clarity in Od1 row. | 2016-02-01 PACT/XAAEP Lisa Alm
O | - | No changes, ready for approval. | 2016-02-01 PAPR/XAAEP Ulrika Nilsson
Pd1 | All | PRC#714 : Add R at Project Manager for Q & Safety Plan and Quality plan for project. Change R for Q & safety compliance plan. PRC#715 : Add I at Test Responsible for User Documentation PRC#635 : Add for Safety Manual & Reliability Manual R for SE and C for productization. Added description that where more than one person is assigned, only relevant persons should be invited. Clarified that only RACI roles needs to be included in Names on RACI, not all project roles. Changed from Viewpoints to RACI roles in "Invite example RACI". PRC#479 : Added EX Responsible RACI role and EX viewpoint. PRC#526 : Added Scrum Master, Product Owner Product Architect renamed to Architect (SW/HW) Remove Quality Manager, will be covered by QA Person Remove Technical coordinator,SW Analyst och HW analyst. These will be covered by Architect (SW/HW) Remove product line manager och System product line manager. These will be covered by Product Manager och Technical Product manager Info regarding delegation added in the Help sheet | 2016-11-07 PAPR/XAAEP Ulrika Nilsson
Pd2 |  | OpenText premigration activity: Property TAG added. Ref PCR#893(ALM:Process_Change_Management) | 2017-07-13 CTQO Karin Myrehed
Pd3 | All | Updated after formal review. Removed Scrum Master, Architect (HW/SW) and Product Owner. Reinserted Technical Coordinator, Software Analyst and HW Analyst. PRC#740: Security viewpoint added for PTTD in "Roles - Viewpoints" PRC#802: Remove required drafts before G2 and G3 of the Architecture Baseline, Functional Baseline, Design Baseline and Test Description Baseline. PRC#870: Added C for TPM for SVTD and SVTR in "RACI" PRC#868: Added C for CM on Final Conclution of Test | 2017-08-21 IACT/CTAEP Ulrika Nilsson
Pd4 | All | Updated acc to review record. Review invitation text updated. | 2017-10-04 IACT/CTAEP Ulrika Nilsson
Pd5 | All | Updated according to Review record. | 2017-12-14 IACT/CTAEP Ulrika Nilsson
P |  | No changes, ready for approval. | 2017-12-20 IACT/CTACS Christina Persson
Qd1 | RACI, Names on RACI, Invite Example - RACI, Overview, Help, Invite Example - Viewpoints | #1266: Removed the Q & Safety Compliance Plan #1318: Added the following for Test Summary and Final CoT (Final CoT): C for Test Responsible, I for Cyber security Engineer and I for EX Responsible. #1013: Added excel template for Requirement traceability matrix. #972: Added I for Quality plan to be the same as for Q&Safety plan. removed C for Safety engineer for Quality plan. Changed text within parentesis after Q&Safety plan to (for safety projects). Removed comment "for safety projects" on the C for SA for Q&Safety Plan. Added word template for Quality Plan. Change to safety in the project column for Q&Safety plan. Changed skeleton to template. #738: Updated for Skribenta. Added Released User Documentation as a separate row. Added comment for user and product guide and Release note "The Names on RACI for the system project shall be used for System Documents". Removed PjM Documentation and Technical Writer. Added Skribenta User Doc Team Lead. Removed cell notes regarding templates in two "where to find" cells. #1127: Architecure Baseline changed to draft to G2, Design Baseline changed to draft at G3, Test Description Baseline changed to draft at G3. #1158: Updated for document based on checklist for Beta, IVA and start of Type Test, renamed to correspod to sheet names in the checklist, reorder to be the same order as in the checklist, added C for Test responsible for STT and RAT checklist, added excel template in the “where to find” field. #1189: Added draft at G3 for Test description baseline and comment "Shall be approved before start of formal test which for some test levels are before G4." #1333: Removed links to documents, changed ABB templates to Templates. #1282: Added row for Component Specification. #1227: Cyber Security Assessment added. | 2019-10-02 IAPCP/REP Ulrika Nilsson
Qd2 | Help, Overview, RACI, Guidance | #1181: T3 Tool Defect Analysis added. Updated according to review record. | 2019-10-18 IAPCP/REP Ulrika Nilsson
Qd3 | Overview, RACI | Updated according to review record. | 2019-11-13 IAPCP/REP Ulrika Nilsson
Q | - | No changes, ready for approval. | 2019-11-15 IAPCP/ACS Christina Persson
Sd1 | - | Document updated to Open Text format according to 3BSE093500, with content from approved ECM revision Q • Template List: PCR: 1375 • Other changes: No | 2019-12-04 IAPCP Peter Mooe
Sd2 | Template Revision history | Removed skeleton document ID and revision in row 3 in sheet Template Revision history. | 2020-01-20 IAPCP/RER Ulrika Nilsson
S |  | Approved version
Td1 | Overview, RACI | #1422: Tab RACI - Removed row 28 Product Integration Plan which is withdrawn. Removed the Reset filter button and the macro. #1357: Added Cyber Security Threat Model on row 54 #1274: Added Ex Application Report (Technical Report) on row 107 #1353 Row 44 Component Specification - added additional text to the comment Also added row 100 T3 Tool Defect Analysis to verview where it was missing. | 2020-05-01 IAPCP/RCB Birthe W. Shelton
Td2 | Overview, RACI | Updated according to review comments in 3BSE039313-RR rev Pd1 | 2020-05-04 IAPCP/RCB Birthe W. Shelton
Td3 |  | Updated according to comment from change check | 2020-08-20 IAPCP/RCB Birthe W. Shelton
Td4 | RACI | #1484: For General Export Control Input Data Report (input to ECA) Removed Word-templates from the column "Where to Find". Replaced the comment ECA- Export Control Accountable with PCE - Product Classification Engineer. | 2020-08-21 IAPCP/RCB Birthe W. Shelton
Td5 | RACI | #1484: Replaved ECA with PCE also in column A. | 2020-08-26 IAPCP/RCB Birthe W. Shelton